## Project Timeline
Workstream | Task | Owner | Start Day | Duration | End Day | Dependency | Deliverable | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Case analysis | Validate source, scope, and business question | System Analyst | 1 | 1 | 1 |  | Case brief | Done | bar: Day 1
Data preparation | Prepare anonymized complaint sample | Analyst | 2 | 1 | 2 | Case brief | Sample CSV + staging SQL | Done | bar: Day 2
Data analysis | Review category, SLA, severity, channel, and closure patterns | Analyst | 3 | 1 | 3 | Sample CSV | Data exploration summary | Done | bar: Day 3
Business analysis | Convert findings into current gaps and system needs | Business/System Analyst | 4 | 1 | 4 | Data exploration | Gap analysis | Done | bar: Day 4
Process design | Define target workflow, SOP, status lifecycle, and roles | System Analyst | 5 | 1 | 5 | Gap analysis | Workflow + SOP | Done | bar: Day 5
Requirements | Write user stories, FR/NFR, and business rules | System Analyst | 5 | 1 | 5 | Workflow | Requirements | Done | bar: Day 5
Data modelling | Design ERD, data dictionary, and relationships | System Analyst | 6 | 1 | 6 | Requirements | ERD + data dictionary | Done | bar: Day 6
Schema design | Prepare SQL schema and developer notes | System Analyst + Developer | 7 | 1 | 7 | ERD | SQL schema | Done | bar: Day 7
Testing | Prepare acceptance criteria, UAT, and traceability | QA + System Analyst | 8 | 1 | 8 | Requirements | UAT + traceability | Done | bar: Day 8
Project planning | Review timeline, backlog, dependencies, and risks | System Analyst | 9 | 1 | 9 | All analysis docs | Project plan | Done | bar: Day 9
Final review | Clean repository and finalize README | System Analyst | 10 | 1 | 10 | All deliverables | Final repository | Done | bar: Day 10

## Backlog
ID | Backlog item | Priority | Owner | Estimate | Output
BL-01 | Import complaint record sample | Must Have | Developer | S | Complaint records stored
BL-02 | Identify ticket candidate complaint | Must Have | Developer | S | Ticket candidate flag
BL-03 | Map complaint category and severity | Must Have | System Analyst + Developer | M | Internal category + severity
BL-04 | Generate SLA due date | Must Have | Developer | M | Due date and overdue logic
BL-05 | Create service recovery ticket | Must Have | Developer | M | Ticket linked to complaint
BL-06 | Assign ticket owner/PIC | Must Have | Developer | S | Owner assignment
BL-07 | Submit investigation note | Must Have | Outlet Manager | S | Root cause note
BL-08 | Submit recovery action | Must Have | Outlet Manager | S | Recovery action record
BL-09 | Review and approve/reject closure | Must Have | Manager / QA | M | Review decision
BL-10 | Track status history | Must Have | Developer | M | Status audit trail
BL-11 | Monitor overdue tickets | Should Have | Manager / QA | M | Overdue monitoring
BL-12 | Flag repeat issue by outlet and category | Should Have | Manager / QA | M | Repeat issue flag
BL-13 | Add dashboard summary | Could Have | Analyst / BI | M | Management summary

## Risks
Risk | Impact | Control | Owner | Status
Complaint descriptors are text-heavy | Category mapping can be inconsistent | Use simple MVP category rules and refine with feedback | System Analyst | Open
SLA logic varies by severity | Due date rules can be disputed | Document assumptions and allow configuration | System Analyst | Open
Ownership unclear between outlet and QA | Ticket delay or duplicate handling | Define default routing by category and severity | Area Manager | Open
Closure approved without evidence | Recovery action may not be verifiable | Require review note or evidence reference for closure | QA / Manager | Open
Repeat issues not escalated | Root cause can recur | Flag repeated outlet/category combination | Area Manager | Open

## Sources
Source | Usage in project | URL
NYC Open Data — 311 Service Requests from 2020 to Present | Primary public complaint data reference | https://data.cityofnewyork.us/Social-Services/311-Service-Requests-from-2020-to-Present/erm2-nwe9
NYC311 — Food Safety Complaint | Business context for food establishment complaint types | https://portal.311.nyc.gov/article/?kanumber=KA-01111
ISO 10002:2018 — Guidelines for complaints handling in organizations | Reference for complaint handling process and improvement logic | https://www.iso.org/standard/71580.html