## Project Timeline
Workstream | Start Day | Duration | Owner | Main Output | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Case and source validation | 1 | 1 | System Analyst | Case brief and source list | bar: Day 1
Data exploration | 2 | 2 | System Analyst | Data findings and ticket candidate logic | bar: Day 2 to Day 3
Gap analysis | 4 | 1 | System Analyst | Current condition, pain point, system need | bar: Day 4
Workflow, SOP, and requirements | 5 | 2 | System Analyst | To-Be workflow, SOP, FR/NFR | bar: Day 5 to Day 6
ERD and data model | 7 | 1 | System Analyst | ERD, data dictionary, business rules | bar: Day 7
UAT and traceability | 8 | 1 | System Analyst | Acceptance criteria, UAT scenarios, traceability matrix | bar: Day 8
Developer handoff | 9 | 1 | System Analyst | API discussion points, validation rules, edge cases | bar: Day 9
Final documentation review | 10 | 1 | System Analyst | README, diagrams, timeline, and source notes checked | bar: Day 10

## Backlog
ID | Backlog Item | Priority | Owner | Effort | Notes
B-01 | Import inspection records | Must Have | Developer | Medium | CSV upload or API sync can be discussed.
B-02 | Detect failed / conditional inspection records | Must Have | Developer | Small | Use inspection result field.
B-03 | Create corrective action ticket | Must Have | Developer | Medium | Ticket links to violation and inspection record.
B-04 | Assign PIC and due date | Must Have | QA / Area Manager | Small | Priority and SLA based on risk level.
B-05 | Submit correction evidence | Must Have | Outlet Manager | Medium | Evidence linked to ticket history.
B-06 | QA approve or reject evidence | Must Have | QA | Medium | Closure requires QA approval.
B-07 | Monitor open and overdue tickets | Should Have | Management | Medium | Used for operational visibility.
B-08 | Flag repeated issues | Should Have | Area Manager | Medium | Used for escalation review.

## Risks
Risk | Impact | Mitigation
Scope expands into POS, inventory, or ERP | Project becomes too broad | Keep the MVP limited to corrective action workflow.
Violation notes are unstructured | Issue categorization may be inconsistent | Use simplified MVP categories and refine later with stakeholders.
Due-date rules are too generic | SLA may not reflect real policy | Mark SLA rules as assumptions until stakeholder validation.
Evidence approval flow is unclear | Ticket closure can become weak | Require QA approval before Closed status.
Technical details are hard to follow | Decisions may be missed | Use summary tables, diagrams, and clear handoff notes.

## Sources
Source | URL | Use
City of Chicago Food Inspections Dataset | https://data.cityofchicago.org/Health-Human-Services/Food-Inspections/4ijn-s7e5 | Primary public dataset
City of Chicago Dataset Metadata API | https://data.cityofchicago.org/api/views/4ijn-s7e5 | Dataset metadata reference
NYC Health Restaurant Grades | https://www.nyc.gov/site/doh/services/restaurant-grades.page | Business context
FDA Inspections to Protect the Food Supply | https://www.fda.gov/food/compliance-enforcement-food/inspections-protect-food-supply | Process and corrective action context